## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [12 empty] | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Iteration 1: Planning
Project Initiation | Architecture |  |  |  |  | 1 |  | 1
|  | Design architecture | Project Manager, Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 1 |  | 1 | [5 empty] | 0
| Requirements |  |  |  |  | 3 |  | 4 |  |  |  |  | 0
|  | Needs analysis - DB architecutre | architect | Ryan Shepherd | 1 |  | 2 | [5 empty] | 0
|  | Needs analysis - network architecture | architect | Andrew Taylor | 1 |  | 1 | [5 empty] | 0
|  | Needs analysis - cloud and security | architect | Liam Floyd | 1 |  | 1 | [5 empty] | 0
| Documentation |  |  |  |  | 5 |  | 18 |  |  |  |  | 0
|  | Project Charter | Project Manager, Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 2 |  | 6 | [5 empty] | 0
|  | Requirements Document | Project Manager, Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 3 |  | 12 | [5 empty] | 0
0
Iteration 2: | Group Tasks |  |  |  |  | 13 |  | 0 |  |  |  |  | 0
Scheduling and research |  | Project Plan | Project Manager, Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 10 | [7 empty] | 0
|  | Risk assesment | Project Manager, Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 3 | [7 empty] | 0
| Network Component |  |  |  |  | 4 |  | 0
|  | Research network hardware | Architect | Andrew Taylor | 2
|  | Research connecting sites | Architect | Andrew Taylor | 2 | [7 empty] | 0
|  | Research network security protocols | Architect | Andrew Taylor | 2
| DB and Cluster Component |  |  |  |  | 4 |  | 0
|  | Research Cluster hardware | Architect | Ryan Shepherd | 2 | [7 empty] | 0
|  | Research DB Security Protocols | Architect | Ryan Shepherd | 2 | [7 empty] | 0
| Security and hosted cloud services |  |  |  |  | 6 |  | 0 |  |  |  |  | 0
|  | Research cloud services - Azure, AWS, Google | Architect | Liam Floyd | 2 | [7 empty] | 0
|  | Research network security hardware | Architect | Liam Floyd | 2
|  | Research intrusion detection systems | Architect | Liam Floyd | 2 | [7 empty] | 0
Tentative IT3: Database | Design |  |  |  |  | 12 |  | 0 |  |  |  |  | 0
|  | ER diagram | Architect |  | 2 | [7 empty] | 0
|  | Risk analysis | Architect |  | 1 | [7 empty] | 0
|  | Database analysis | Architect |  | 1 | [7 empty] | 0
|  | Research clustering | Architect |  | 4 | [7 empty] | 0
Architecture Document
|  | Design Cluster | Architect |  | 4 | [7 empty] | 0
| Development |  |  |  |  | 22 |  | 0 |  |  |  |  | 0
|  | Review requirements | Architect |  | 1 | [7 empty] | 0
|  | write mySql code | Architect |  | 6 | [7 empty] | 0
|  | Build front-end of DB | Architect |  | 6
|  | spec out cluster | Architect |  | 5 | [7 empty] | 0
|  | Build cluster | Architect |  | 4 | [7 empty] | 0
| Analysis |  |  |  |  | 5 |  | 0 |  |  |  |  | 0
|  | System Testing | Architect |  | 2 | [7 empty] | 0
|  | Bug fix as required | Architect |  | 2 | [7 empty] | 0
|  | Evaluate needs for next iteration | Project Manager |  | 1 | [7 empty] | 0
Tentative IT4: Cloud, Security | Design |  |  |  |  | 9 |  | 0 |  |  |  |  | 0
|  | Research Hosting services | Architect |  | 3 | [7 empty] | 0
|  | Risk analysis | Project Manager |  | 1 | [7 empty] | 0
|  | Research network security/needs analysis | Architect |  | 2 | [7 empty] | 0
|  | Research intrusion detection | Architect |  | 3 | [7 empty] | 0
|  | needs analysis on hosting services | Architect |  | 1
| Development |  |  |  |  | 17 |  | 0 |  |  |  |  | 0
|  | Review security requirements | Architect |  | 1 | [7 empty] | 0
|  | Build web filtering and firewall security | Architect |  | 5 | [7 empty] | 0
|  | Implement intrusion detection | Architect |  | 5 | [7 empty] | 0
|  | Spec out/design cloud hosting | Architect |  | 3 | [7 empty] | 0
|  | Design cloud email server | Architect |  | 3 | [7 empty] | 0
| Analysis |  |  |  |  | 6 |  | 0 |  |  |  |  | 0
|  | Build report | Architect |  | 6 | [7 empty] | 0
0
Total |  |  |  |  | 110 | 107 | 0 | 23 | 0 | 0 | 0 | 0 | 0