## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [12 empty] | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 1 |  | 0
|  | Design architecture | Project Manager | Ryan Shepherd | 1 | [7 empty] | 0
| Requirements |  |  |  |  | 3 |  | 0 |  |  |  |  | 0
|  | Gather | Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 1 | [7 empty] | 0
|  | Analyze | Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 1 | [7 empty] | 0
|  | Specify | Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 1 | [7 empty] | 0
| Documentation |  |  |  |  | 13 |  | 0 |  |  |  |  | 0
|  | Project Charter | Project Manager | Ryan Shepherd | 2 | [7 empty] | 0
|  | Requirements Document | Project Manager, Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 3 | [7 empty] | 0
|  | Project Plan | Project Manager, Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 4 | [7 empty] | 0
|  | Architecture Document | Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 4 | [7 empty] | 0
0
Networking | [12 empty] | 0
Iteration 1: | Design |  |  |  |  | 12 |  | 0 |  |  |  |  | 0
|  | Needs analysis | Architect | Ryan Shepherd | 4 | [7 empty] | 0
|  | Research hardware | Architect | Andrew Taylor | 4 | [7 empty] | 0
| Development |  |  |  |  | 4 |  | 0
|  | Map the sites | Architect | Liam Floyd | 2 | [7 empty] | 0
|  | Place routers and boosters | Architect | Liam Floyd | 1 | [7 empty] | 0
|  | Intersite link design | Architect | Ryan Shepherd, Andrew Taylor | 1 | [7 empty] | 0
| Analysis |  |  |  |  | 2 |  | 0 |  |  |  |  | 0
|  | System Testing | Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 1 | [7 empty] | 0
|  | Evaluate needs for next iteration | Project Manager | Ryan Shepherd | 1 | [7 empty] | 0
0
Database | Design |  |  |  |  | 12 |  | 0 |  |  |  |  | 0
Iteration 2: |  | ER diagram | Architect | Andrew Taylor | 2 | [7 empty] | 0
|  | Risk analysis | Architect | Liam Floyd | 1 | [7 empty] | 0
|  | Database analysis | Architect | Andrew Taylor, Liam Floyd | 1 | [7 empty] | 0
|  | Research clustering | Architect | Ryan Shepherd | 4 | [7 empty] | 0
|  | Design Cluster | Architect | Ryan Shepherd | 4 | [7 empty] | 0
| Development |  |  |  |  | 22 |  | 0 |  |  |  |  | 0
|  | Review requirements | Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 1 | [7 empty] | 0
|  | write mySql code | Architect | Andrew Taylor, Ryan Shepherd | 6 | [7 empty] | 0
|  | Build front-end of DB | Architect | Liam Floyd | 6
|  | spec out cluster | Architect | Ryan Shepherd | 5 | [7 empty] | 0
|  | Build cluster | Architect | Ryan Shepherd | 4 | [7 empty] | 0
| Analysis |  |  |  |  | 5 |  | 0 |  |  |  |  | 0
|  | System Testing | Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 2 | [7 empty] | 0
|  | Bug fix as required | Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 2 | [7 empty] | 0
|  | Evaluate needs for next iteration | Project Manager | Ryan Shepherd | 1 | [7 empty] | 0
security, hosted emails | Design |  |  |  |  | 9 |  | 0 |  |  |  |  | 0
Iteration 3: |  | Research Hosting services | Architect | Liam Taylor | 3 | [7 empty] | 0
|  | Risk analysis | Project Manager | Ryan Shepherd | 1 | [7 empty] | 0
|  | Research network security/needs analysis | Architect | Ryan Shepherd | 2 | [7 empty] | 0
|  | Research intrusion detection | Architect | Andrew Taylor | 3 | [7 empty] | 0
|  | needs analysis on hosting services | Architect | Liam Taylor | 1
| Development |  |  |  |  | 17 |  | 0 |  |  |  |  | 0
|  | Review security requirements | Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 1 | [7 empty] | 0
|  | Build web filtering and firewall security | Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 5 | [7 empty] | 0
|  | Implement intrusion detection | Architect | Andrew Taylor | 5 | [7 empty] | 0
|  | Spec out/design cloud hosting | Architect | Liam Floyd | 3 | [7 empty] | 0
|  | Design cloud email server | Architect | Liam Floyd | 3 | [7 empty] | 0
| Analysis |  |  |  |  | 6 |  | 0 |  |  |  |  | 0
|  | Build report | Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 6 | [7 empty] | 0
0
Total |  |  |  |  | 103 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0