## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom)
|  |  | Role | Owner | Estimated | Effort | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals
Iteration 1: Planning
Project Initiation | Architecture |  |  |  |  | 1 |  | 1
|  | Design architecture | Project Manager, Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 1 |  | 1
| Requirements |  |  |  |  | 3 |  | 4
|  | Needs analysis - DB architecutre | architect | Ryan Shepherd | 1 |  | 2
|  | Needs analysis - network architecture | architect | Andrew Taylor | 1 |  | 1
|  | Needs analysis - cloud and security | architect | Liam Floyd | 1 |  | 1
| Documentation |  |  |  |  | 5 |  | 18
|  | Project Charter | Project Manager, Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 2 |  | 6
|  | Requirements Document | Project Manager, Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 3 |  | 12
Iteration 2: | Group Tasks |  |  |  |  | 13 |  | 32
Scheduling and research |  | Project Plan | Project Manager, Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 10 |  | 25
|  | Risk assesment | Project Manager, Architect | Ryan Shepherd, Andrew Taylor | 3 |  | 7
|  | Presentation | Project Manager, Architect | Ryan Shepherd, Andrew Taylor | 6 |  | 7
| Network Component |  |  |  |  | 4 |  | 8
|  | Research network hardware | Architect | Andrew Taylor | 2 |  | 1
|  | Research connecting sites | Architect | Andrew Taylor | 2 |  | 1
|  | Research network security protocols | Architect | Liam Floyd | 2 |  | 0
|  | Network Diagraming | Architect | Andrew Taylor | 3 |  | 6
| DB and Cluster Component |  |  |  |  | 4 |  | 3
|  | Research Cluster hardware | Architect | Ryan Shepherd | 2 |  | 2
|  | Research DB Security Protocols | Architect | Ryan Shepherd | 2 |  | 0
|  | Server cluster design | Architect | Ryan Shepherd | 2 |  | 1
| Security and hosted cloud services |  |  |  |  | 6 |  | 8
|  | Research cloud services - Azure, AWS, Google | Architect | Liam Floyd | 2 |  | 2
|  | Research network security hardware | Architect | Liam Floyd | 2 |  | 4
|  | Research intrusion detection systems | Architect | Liam Floyd | 2 |  | 0
|  | Research Security protocols | Architect | Liam Floyd | 2 |  | 2
IT3: Architecture | Group Activities |  |  |  |  | 20 |  | 39
|  | Architecture Document | Project Manager, Architects | Ryan Shepherd, Andrew Taylor, Liam Floyd | 15 |  | 31
| Network |  |  |  |  | 6 |  | 11
|  | Hardware design | Architect | Andrew Taylor | 1 |  | 2
|  | update diagrams | Architect | Andrew Taylor | 1 |  | 2
|  | write detailed report | Architect | Andrew Taylor | 2 |  | 2
|  | detail Windstream choice | Architect | Andrew Taylor | 1 |  | 2
|  | configuration info | Architect | Andrew Taylor | 1 |  | 3
| Database |  |  |  |  | 19 |  | 7
|  | ER Diagram | Architect | Ryan Shepherd | 3 |  | removed
| Server systems |  |  |  |  | 24 |  | 13
|  | Hardware recommendations | Architect | Ryan Shepherd | 3 |  | 1
|  | Configuration information | Architect | Ryan Shepherd | 2 |  | 1
|  | Write report | Architect | Ryan Shepherd | 4 |  | 1
|  | Update diagrams | Architect | Ryan Shepherd | 1 |  | 1
| Cloud services |  |  |  |  | 14 |  | 9
|  | Service provider services, price comparison | Architect | Liam Floyd | 3 |  | 3
|  | Compare cloud infrastructure instead of on-prem server cluster | Architect | Liam Floyd, Ryan Shepherd | 3 |  | 0
| Security Services |  |  |  |  | 8 |  | 6
|  | Hardware recomendation | Architect | Liam Floyd | 5 |  | 3
|  | Layers of security protocols | Architect | Liam Floyd, Ryan Shepherd | 1 |  | 3
|  | Configuration and settings information | Architect | Liam Floyd | 2 |  | 0
Iteration 4: Architecture updated | Group Activities |  |  |  |  | 23 |  | 44
|  | Final Architecture Report Revisions | Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | 15 |  | 22
|  | Beginning final presentation | Project Manager, architects | Ryan Shepherd, Andrew Taylor, Liam Floyd | 5 |  | -
|  | ER Diagram | Architect | Ryan Shepherd | 3 |  | 4
|  | Cloud server structure | Architect | Ryan Shepherd | 4 |  | 3
|  | cloud costs | Architect | Liam Floyd | 3 |  | 5
|  | Comparison of cloud service providers | Architect | Liam Floyd | 5 |  | 4
|  | Final budget costs | Project Manager, Architects | Ryan Shepherd, Andrew Taylor, Liam Floyd | 5 |  | 3
|  | Intrusion Detection hardware | Architect | Liam Floyd | 2 |  | 3
|  | any other diagram updates | Architect | Ryan Shepherd, Andrew Taylor, Liam Floyd | - |  | -
Iteration 5: wrap-up | Group Activities |  |  |  |  | 28 |  | 12
|  | Test Plan | Project Manager, Architects | Ryan Shepherd, Andrew Taylor, Liam Floyd | 6 |  | 5
|  | User/System Guide | Project Manager, Architects | Ryan Shepherd, Andrew Taylor, Liam Floyd | 10 |  | 5
|  | Final Presentation | Project Manager, Architects | Ryan Shepherd, Andrew Taylor, Liam Floyd | 10 |  | In Process
|  | Project Results | Project Manager | Ryan Shepherd | 2 |  | 2
Total |  |  |  |  | 169 | 178 |  | 215